## DTRC
Test Case Name: | DTR CORRECTION – TEST CASES
Module Name: | Requisition Module
Created by: | Jared Vicente
Date Creation: | December 2, 2025
TEST CASE ID | TEST SCENARIO | PRE-CONDITION | TEST STEPS | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS (PENDING/PASS/FAIL
TC_DTR_001 | Successful DTR Correction Request | User has access to DTR correction | 1. Open DTR Correction 2. Select date 3. Enter valid Time In & Time Out 4. Enter reason 5. Submit 6. Approver 1 approves 7. Approver 2 approves | Date: Dec 2 Time In: 08:00 Time Out: 17:00 Reason: Forgot to time-in | Request saved and routed to 2 approvers; final status = Approved | As expected – request saved, routed to both approvers, and final status updated to Approved. | Pass
TC_DTR_002 | Approver 1 Approves, Approver 2 Disapproves | DTR Correction must be pending approval | 1. Submit request 2. Approver 1 approves 3. Approver 2 Disapproves | Date: Jan 10 Time In: 08:00 Time Out: 17:00 Reason: Forgot to time-in | Request final status = Disapproved; Disapproveion reason visible | Request was successfully marked as Disapproved, and the Disapproveion reason is displayed correctly to the User. | Pass
TC_DTR_003 | Approver 1 Disapproves Immediately | Request awaiting Approver 1 | 1. Submit DTR correction 2. Approver 1 Disapproves | Reason: “Test Disapproved” | Status becomes Disapproved; Approver 2 cannot act | Request status was successfully updated to Disapproved, and Approver 2 cannot act on the request. | Pass
TC_DTR_004 | Invalid Time Range | User on DTR correction screen | 1. Enter Time Out earlier than Time In 2. Submit | Time In: 09:00 Time Out: 08:00 | When the user selects a Time In, automatically restrict the Time Out options to only be after the selected Time In | Selecting a Time In correctly restricts Time Out options, allowing only times later than the selected Time In | Pass
TC_DTR_005 | Date Limited by Selected Corrected Date | User on DTR correction screen | 1. Select a corrected date (e.g., 2025-12-03) 2. Open the Time In picker 3. Check the date selection options in the picker if limited based on the corrected date | Corrected Date: 2025-12-03 Attempted Time In Date: 2025-12-04 (invalid) | Time In picker cannot select a date beyond the corrected date | Date picker restricts selection to not go beyond the corrected date | Pass
TC_DTR_006 | Duplicate Request for Same Date | User already filed correction for date | 1. Submit new DTR correction for same date | Date: Dec 2 (already used) | System blocks with message: “Request already submitted for this date” | System allows submitting the DTR correction request again for the same date, creating a duplicate entry instead of blocking it | Fail
TC_DTR_007 | Request Finalized – User Cannot Edit | Request already approved/Disapproveed | 1. Open completed request 2. Attempt to do an action | None | The Approve and Disapprove buttons are not visible; no edits can be made to the request | The buttons function as intended, the request cannot be edited, and the status updates properly after approval or disapproval | Pass
TC_DTR_008 | Request Not Visible for Unauthorized Approver | A DTR correction request exists, and the user viewing it is not an assigned approver | 1. Log in as a user who is not an assigned approver 2. Navigate to the DTR Correction Requests page 3. Observe the list of requests displayed | Any existing DTR correction request and not assigned approvers account | The request does not appear in the approver’s request list | Request not visible to unauthorized approver; the approver’s request list only shows requests they are assigned to | Pass
TC_DTR_009 | Resubmission After Disapproveion | After Disapproveion: User has Disapproveed request | 1. Submit new DTR correction for same date | Date: Dec 2 (previously Disapproveed) | System allows new request with the same date as long as Disapproveed | System successfully submits a new DTR correction request with the same date as an existing Disapproveed request. Duplicate requests are allowed since no validation is in place regardless of the status | Partially Pass
TC_DTR_010a | Request Cancellation Before First Approval | A DTR correction request has been submitted and is pending approval from Approver 1 | 1. User submits a DTR correction request 2. User cancels the request before Approver 1 approves 3. Observe the request visibility and status for Approver 1 | Any pending DTR correction request | Request status shows Cancelled to Approver 1. Approve and Disapprove buttons are disabled/hidden | Request displays as Cancelled to Approver 1; action buttons are disabled | Pass
TC_DTR_010b | Request Cancellation After First Approval | A DTR correction request has been submitted and approved by Approver 1, pending approval from Approver 2 | 1. User submits a DTR correction request 2. Approver 1 approves the request 3. User cancels the request after Approver 1 approval 4. Observe the request visibility and status for Approver 2 and Approver 1 | Any approved by Approver 1 DTR correction request | Request status shows Cancelled to Approver 2. Approver 1’s approval remains recorded approved. Approve and Disapprove buttons are disabled | Request displays as Cancelled to Approver 2; Approver 1’s approval remains recorded approved; action buttons are disabled | Pass
TC_DTR_011 | Approver Disapproves Without Reason | Approver required to input reason | 1. Approver clicks Disapprove 2. Leave reason blank 3. Submit | Any pending DTR correction request | System prevents submission by showing error message; requires Disapprove reason | System prevents submission and shows modal | Pass
TC_DTR_016 | Pending Requests Section | User has submitted requests pending approval | 1. Go to DTR Correction section 2. Open Pending tab | Requests awaiting approver action | Only requests with status Pending are listed | All pending requests are displayed correctly under the Pending tab | Pass
TC_DTR_017 | Approved Requests Section | Some requests fully approved | 1. Go to DTR Correction section 2. Open Approved tab | Requests with both approvers approved | Only requests with status Approved are listed | All approved requests are shown correctly under the Approved tab | Pass
TC_DTR_018 | Disapproved/Disapproveed Requests Section | Some requests Disapproveed | 1. Go to DTR Correction section 2. Open Disapproved tab | Requests Disapproveed by any approver | Only requests with status Disapproveed/Disapproved are listed | All Disapproveed requests are displayed correctly in the Disapproved tab | Pass
TC_DTR_019 | Cancelled Requests Section | Some requests cancelled by user | 1. Go to DTR Correction section 2. Open Cancelled tab | Requests cancelled by user | Only requests with status Cancelled are listed | All cancelled requests are displayed correctly in the Cancelled tab | Pass
TC_DTR_020 | Pending Request Visibility per Approver | A DTR correction request is submitted and awaiting approval from Approver 1 | 1. Submit a new DTR correction request 2. Log in as Approver 1 and check pending requests 3. Log in as Approver 2 and check pending requests | Any new pending DTR correction request | The request is visible to Approver 1 only and not visible to Approver 2 until Approver 1 approves | The request is correctly visible only to Approver 1; Approver 2 cannot see it until approved by Approver 1 | Pass
TC_DTR_021 | Prevent Submission When Date Already Has a Pending DTR Request | User already has a Pending DTR correction request for the same date | 1. Submit DTR correction (Pending) 2. Submit a second DTR correction for the same date | Date: Dec 2 (already has Pending request) | System should block submission with: "A pending request already exists for this date." | System allows duplicate submission even though date is already pending | Fail
TC_DTR_022 | Prevent Submission When Date Already Has an Approved DTR Request | User already has an Approved request for same date | 1. Submit DTR correction request 2. Approver 1 & 2 approve 3. User submits another request for same date | Date: Dec 3 (already Approved) | System should block submission with: "This date already has an approved request." | System still allows submission despite existing Approved request | Fail
TC_DTR_023 | Prevent Overlapping DTR Requests for Same Date After Time Changes | User has an existing DTR correction request for that day | 1. Submit DTR correction for Dec 4 2. Submit new DTR correction for Dec 4 (different time values) | Existing Request: Dec 4 (08:00–17:00)New Request: Dec 4 (09:00–18:00) | System should detect same-date conflict and block submission | System accepts second request even with overlapping date | Fail
TC_DTR_024 | Resubmission Should Be Allowed After Cancellation | User had a DTR request but cancelled it | 1. Submit DTR correction for Dec 5 2. Cancel request 3. Submit new DTR correction for Dec 5 | Date: Dec 5 | System should allow new submission because status is Cancelled | System allows submission successfully | Pass
TC_DTR_025 | System Must Validate Date Before Validating Time | Date already used in existing request | 1. Choose a date used previously 2. Enter Time In and Time Out 3. Submit | Date: Dec 2 (duplicate)Time In: 08:00Time Out: 17:00 | System should detect date conflict first and block before time validation | System processes time validation first; duplicate date validation never executed | Fail
TC_DTR_026 | System Should Check Conflict Even If Reason Is Different | User already has a DTR correction for the same date | 1. Submit DTR Correction for Dec 10 (Reason A) 2. Submit another DTR Correction for Dec 10 (Reason B) | 2010-12-01 | Should block because date already used | System accepts regardless of the reason because there's no validation for checking | Fail
TC_DTR_027 | Validation Should Trigger Before Attachment Upload | Duplicate date chosen | 1. Choose a date already used in existing DTR correction 2. Attempt to submit before attaching file | 2005-12-01 | System should show conflict error before attachment validation | System accepts regardless of the attachment because there's no validation for checking | Fail